## Risk Matrix
RISK MATRIX |  |  | LIKELIHOOD
|  |  | Rare | Unlikely | Possible | Likely | Almost Certain
|  | (description) | student to provide a description | student to provide a description | student to provide a description | student to provide a description | student to provide a description
CONSEQUENCE | Severe | student to provide a description | HIGH | VERY HIGH | VERY HIGH | EXTREME | EXTREME
| Major | student to provide a description | HIGH | HIGH | VERY HIGH | VERY HIGH | EXTREME
| Moderate | student to provide a description | LOW | MEDIUM | MEDIUM | HIGH | VERY HIGH
| Minor | student to provide a description | VERY LOW | LOW | MEDIUM | MEDIUM | HIGH
| Insignificant | student to provide a description | VERY LOW | VERY LOW | LOW | MEDIUM | MEDIUM

## Risk Assessment
Context - Asset(s) that we are trying to protect
1. Asset: Customer Data, Description: Personally Identifiable Information (PII), financial details, login credentials. Perceived Value / Business Impact: Personally Identifiable Information (PII), financial details, login credentials. Potential Breaches: Data breaches, identity theft, financial fraud. 2. Asset: Financial Information. Description: Banking details, payroll, internal financial records. , Perceived Value/ Business Impact: Very High – Direct financial losses, fraud, or account manipulation., Potential Risks: Ransomware attacks, insider threats, fraud. 3. Asset: Intellectual Property (IP). Description: Proprietary research, software code, trade secrets., Perceived Value/ Business Impact: High – Loss could impact competitive advantage and revenue., Potential Risks: Data theft, espionage, insider threats. 4. Asset: IT Infrastructure. Description: Servers, databases, cloud storage, network devices. , Perceived Value/ Business Impact: High – Downtime could disrupt operations, affecting revenue and productivity., Potential Risks: Denial-of-Service (DoS) attacks, misconfigurations, unauthorized access. 5. Asset: Business Reputation Description: Brand trust, customer relationships, and shareholder confidence., Perceived Value/ Business Impact: Priceless – A security breach can severely damage reputation, affecting long-term success., Potential Risks: Phishing, social engineering, data leaks.
Risk |  |  |  |  | Inherent Risk Rating |  |  | Current Risk Rating |  |  |  |  | Target Risk Rating
ID | Title | Description | Sources or Causes of Risk | Consequences of Risk | Likelihood | Consequence | Risk Level | Existing control measures | Effectiveness of exisitng control measures | Likelihood | Consequence | Risk Level | Additional control measures | Effectiveness of additional control measures | Likelihood | Consequence | Risk Level
R01 | Phishing Attack | A malicious email tricks employees into revealing credentials, leading to unauthorized access. | Targeted phishing emails, lack of employee awareness. | Compromised accounts, data breaches, financial losses. | Almost Certain | Severe | EXTREME | Email filtering, antivirus, employee awareness training. | Moderate. The threats are more likely to harm the users. | Possible | Severe | VERY HIGH | Treat Multi-Factor Authentication (MFA), advanced phishing simulations | Excellent - MFA prevents unauthorized access, phishing simulations improve employee awareness. | Rare | Minor | VERY LOW
R02 | Ransomware Attack | Malware encrypts critical files, demanding ransom for decryption. ¦ Unpatched software, malicious email attachments. | Unpatched software, malicious email attachments. | Data loss, financial harm, operational disruption. | Almost Certain | Severe | EXTREME | Regular backups, endpoint protection, firewalls. | Good Although measures are sufficient, there are further space for the threats. | Possible | Moderate | MEDIUM | Treat - Network segmentation, Zero Trust security model. | Excellent - Network segmentation limits spread, Zero Trust enhances access control. | Rare | Moderate | LOW
R03 | Insider Threat - Negligence | An employee misconfigures cloud storage, exposing sensitive data. | Poor access controls, lack of training. | Data leakage, compliance violations, reputational damage. | Possible | Moderate | MEDIUM | Role-Based Access Control (RBAC), security policies. | Moderate The insider threat are inevident in any organization. | Rare | Moderate | LOW | Treat - Continuous monitoring, real-time alerts for misconfigurations. | Good - Continuous monitoring detects misconfigurations, automated alerts reduce human error. | Unlikely | Minor | LOW
R04 | Denial-of-Service Attack | Attackers overwhelm network resources, causing downtime. | Unprotected servers, lack of DDoS mitigation. | Service disruption, revenue loss. | Possible | Moderate | MEDIUM | Firewalls, rate-limiting, incident response plan. | Good Additional requirement for Cloud based security is required. | Possible | Moderate | MEDIUM | Transfer - Cloud-based DDoS protection services (CDN, Web Application Firewall). | Excellent - Cloud-based DDoS protection ensures availability, CDN mitigates high-traffic attacks. | Rare | Insignificant | VERY LOW
R05 | Credential Theft via Dark Web | Leaked credentials are used to gain unauthorized access. | Employees reusing passwords, previous breaches. | Account takeover, business email compromise. | Likely | Severe | EXTREME | Password policies, dark web monitoring. | Moderate Physical security authentication standards are required. | Possible | Severe | VERY HIGH | Avoid - Enforce password managers, biometric authentication, regular credential monitoring & rotation. | Good - Password managers reduce reuse risks, biometric authentication strengthens security. | Unlikely | Minor | LOW
Note on L6: Excellent Control - Highly effective and very fit for purpose. It substantially reduces the likelihood and/or consequence of the risk. It is cost effective. Good Control - Effective and fit for purpose. It reduces the likelihood and/or Consequence of the risk. It is relatively cost effective. Moderate Control - Moderately effective in reducing likelihood and/or consequence. May be able to be improved. May not be entirely cost effective. Weak Control - Does not exist, or is inadequate, ineffective or marginally effective in reducing likelihood and/or consequence. It is not cost effective
Note on R6: Excellent Control - Highly effective and very fit for purpose. It substantially reduces the likelihood and/or consequence of the risk. It is cost effective. Good Control - Effective and fit for purpose. It reduces the likelihood and/or Consequence of the risk. It is relatively cost effective. Moderate Control - Moderately effective in reducing likelihood and/or consequence. May be able to be improved. May not be entirely cost effective. Weak Control - Does not exist, or is inadequate, ineffective or marginally effective in reducing likelihood and/or consequence. It is not cost effective